PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES	CP/GT/PEC-78/00 rev. 1 corr. 1

2 October 2000

COMMITTEE ON JURIDICAL AND POLITICAL AFFAIRS	Original: Spanish

Working Group on Probity and Public Ethics

work plan of the working group on probity and public ethics

for 2000-2001

(Approved at its meeting of September 28, 2000)

EXPLANATORY NOTE

At its meeting of September 28, 2000, the Working Group on Probity and Public Ethics reviewed and approved the Group’s 2000-2001 Draft Work Plan, presented by the Chair.

The Chair emphasized that the purpose of the plan was to give an indication of the work to be done and that it would be adjusted according to the Group’s needs.

WORK PLAN OF THE

WORKING GROUP ON PROBITY AND PUBLIC ETHICS FOR 2000-2001

| Resolution | Operative paragraph | Mandate | Possible course of action | Tentative dates |
| --- | --- | --- | --- | --- |
| AG/RES. 1723 (XXX-O/00) | 5 | To instruct the Permanent Council to continue to foster the exchange of experiences and information among the OAS and international organizations, the private sector, and civil society organizations, among other pertinent entities, in order to coordinate, strengthen, and identify cooperation activities in the area among the member states. | - Consideration of the regular reports of the General Secretariat | October 2000 |
| AG/RES. 1723 (XXX-O/00) | 6 | To request the Permanent Council to promote the establishment of a specific voluntary fund to finance activities aimed at providing the necessary institutional support to the States Parties for implementing the Inter-American Convention against Corruption. | - General discussion of the establishment of a specific voluntary fund as provided in operative paragraph 6 of resolution AG/RES. 1723 (XXX-O/00) - Drafting of guidelines for the establishment and management of the Fund | January 2001 |
| AG/RES. 1723 (XXX-O/00) | 7 | To instruct the Permanent Council, in following up on the Inter-American Program for Cooperation in the Fight against Corruption, to study corporate social responsibility with a view to defining precisely its scope and content in the inter-American context, to examining and disseminating national and international experiences undertaken to address the issue, and to promoting the exchange of information and experiences among the member states with international financial institutions, other international organizations, the private sector, and civil society organizations. | - General discussion of the topic | October 2000 |
| AG/RES. 1723 (XXX-O/00) | 8 | To instruct the Permanent Council, in following up on the Inter-American Program for Cooperation in the Fight against Corruption, to address, inter alia, the following subjects: training, experience acquired by national institutions, public sector procurement, incompatibilities between public office and private sector interests, and analysis of criminal laws on corruption and related offenses. | - General discussion of the topic | October 2000 |
| AG/RES. 1723 (XXX-O/00) | 9 | To request the Permanent Council to analyze existing regional and international follow-up mechanisms with a view to recommending, by the end of the year, the most appropriate model that States Parties could use, if they think fit, to monitor implementation of the Inter-American Convention against Corruption. That recommendation will be transmitted to the States Parties to the Convention for them to choose the course of action they deem most appropriate. | - Analysis of existing mechanisms and general discussion with a view to making the recommendation requested - Invitation to officials of the Inter-American Drug Abuse Control Commission (CICAD), the Council of Europe, the Caribbean Financial Action Task Force, and the Organisation for Economic Co-operation and Development (OECD) to report on mechanisms used by those organizations | ## September-December |

input.doc

input.doc