PERMANENT COUNCIL OF THE	OEA/Ser.G

ORGANIZATION OF AMERICAN STATES			CP/CAJP-1840/01 rev. 2

12 December 2001

COMMITTEE ON JURIDICAL AND POLITICAL AFFAIRS	Original: Spanish

Working Group on Representative Democracy

DRAFT WORK PROGRAM AND SCHEDULE (2001-2002)

(Approved at the meeting of December 11, 2001)

EXPLANATORY NOTE

At its meeting of December 11, 2001, the Working Group on Representative Democracy considered and approved its Draft Work Program and Schedule for the period 2001-2002.

The Chair underscored that the document was indicative in nature and subject to any necessary changes to allow the Working Group to carry out the mandates entrusted to it.

DRAFT WORK PROGRAM AND SCHEDULE (2001-2002)

| Resolution | Mandate | Proposed courses of action | Estimated dates of meetings | Documents |
| --- | --- | --- | --- | --- |
| AG/RES. 1782 (XXXI-O/01) Operative paragraph 4 | To instruct the Permanent Council, in the context of the dialogue on the modernization of the OAS and the renewal of the inter-American system, to study ways of bringing its political bodies into line with the priority attached to democracy by the Heads of State and Government at the Third Summit of the Americas. | Continue to examine the various arguments for bringing the political bodies into line with the priority attached to democracy. On that basis, draw up the recommendations deemed appropriate. | November 2001– March 2002 | Recommendation and draft resolution Report on the topic |
| AG/RES. 1782 (XXXI-O/01) Operative paragraph 5.a. | Pursue its comprehensive consideration of the topics identified as priorities in the Summits of the Americas process and on the inter-American agenda in terms of the promotion and consolidation of democracy and, for purposes of studying such topics, invite the organs, agencies, and entities of the system, such as the Inter-American Juridical Committee, as well as government and academic experts, and organize special meetings for that purpose, when it deems it necessary. | Hold a special meeting, with an agenda to be decided on by the Working Group. Invite representatives of the organs, agencies, and entities of the system, as well as governmental and academic experts, to participate in one or several meetings of the Working Group. | November 2001 – March 2002 | Recommendation and draft resolution Report on the topic |
| AG/RES. 1782 (XXXI-O/01) Operative paragraph 5.b. | Continue providing any guidance necessary to the General Secretariat with respect to the activities it may carry out in the area of democracy and, in particular, to the UPD, on the basis of the priorities established by the Heads of State and Government in the Summits process and in the inter-American agenda. | Follow-up to General Secretariat activities on that subject. Incorporate recommendations into the corresponding draft resolution. | November 2001 – April 2002 |  |
| AG/RES. 1782 (XXXI-O/01) Operative paragraph 5.c. | Study and approve, by the end of 2001, the UPD Work Plan for 2002, ensuring that said plan includes programs and activities in pursuit of the mandates related to the promotion and consolidation of democracy assigned to the OAS at the Third Summit of the Americas. | Request the UPD to present its Work Plan for 2002 in the third week of November. Study, observations, and comments by delegations. Approval prior to the end of 2001. | November 2001 December 2001 December 2001 | Draft UPD Work Plan Report of the Chair of the Working Group together with its corresponding draft resolution |
| AG/RES. 1782 (XXXI-O/01) Operative paragraph 5.d. | Examine the progress reports on the activities carried out by the UPD in pursuit of the objectives contained in its respective annual Work Plan, including information on the level of budget execution, which will be presented to the pertinent body by the General Secretariat, through appropriate channels, within 45 days following the end of each quarter, and include its comments and observations in its annual report. | Receive the quarterly reports of the UPD, as well as comments thereon by the member states. Prepare recommendations and include them in the corresponding draft resolution. | November 2001-April 2002 April 2002 | Report and corresponding draft resolution |
| AG/RES. 1782 (XXXI-O/01) Operative paragraph 5.e. | Continue studying the updated annual inventory of activities relating to the promotion of democracy in each area of the OAS General Secretariat, and receive detailed oral reports thereon from the person in charge of the area, unit, or office concerned. | Request the UPD to present an updated version of the inventory. Receive the oral report from the UPD Executive Coordinator and, if appropriate, from the representatives in charge of the areas, units, or offices concerned. | February 2002 | Updated inventory |
| AG/RES. 1782 (XXXI-O/01) Operative paragraph 5.f. | Continue studying the implementation of resolution AG/RES. 1637 (XXIX-O/99), "Permanent Specific Fund to Finance Activities Related to OAS Electoral Observation Missions," seeking possible alternatives for the fund’s operation. | Initiate a general discussion on the topic and receive member state observations thereon. Prepare a recommendation for inclusion in the corresponding draft resolution. |  |  |

| Resolution | Mandate | Proposed courses of action | Estimated dates of meetings | Documents |
| --- | --- | --- | --- | --- |
| AG/RES. 1782 (XXXI-O/01) Operative paragraph 7 | Instruct the Permanent Council to report to the General Assembly at its thirty-second regular session on the implementation of this resolution. | Draw up the activity report of the Working Group on Representative Democracy for the period 2001-2002. | April 2002 | Report and draft resolution |

APPENDIX

## MANDATES TO THE GENERAL SECRETARIAT

AG/RES.1782 (XXXI-O/01), “Promotion of Democracy”

[ . . ]

6.	To request the General Secretariat to:

- Consolidate ties and coordination among the various areas, units, and offices for the execution of programs and activities relating to the promotion of representative democracy, and to do so with the collaboration of the various organs, agencies, and entities of the system, so as to give due attention to and fulfill the mandates of the Summits of the Americas and of the General Assembly.

- Propose, through the UPD and in coordination with other units and the organs, agencies, and entities of the system, the inclusion of the specific programs and activities for adequately addressing and complying with the mandates contained in Chapter 1 of the Plan of Action of the Third Summit of the Americas, “Making Democracy Work Better..”

- Incorporate the topics addressed and the concerns raised during the aforementioned special meetings of the Working Group on Representative Democracy, through the UPD, when preparing its work plans and programs.

d.	Regularly update, through the UPD, the annual inventory of activities relating to the promotion of representative democracy.

# Text boxes

CP09080E04.doc

CPSC01105E04

CP09069E04