INTERAMERICAN COMMITTEE ON EDUCATION	OEA/Ser.W/XIII.6.6

VI MEETING OF CIE AUTHORITIES	CIDI/CECIE/doc.6/06

AND EXECUTIVE COMMITTEE						17 April 2006

April 27-28, 2006								Original: Spanish

Washington, D.C.

REGIONAL PROJECT FOR EDUCATIONAL INDICATORS (PRIE)

17th Street and Constitution Avenue, N.W. Washington, D.C. 20006

Project Profile

Name of the Project: Regional Educational Indicators Project (PRIE)

Countries Submitting the Project Proposal: Mexico-the Secretariat for Public Education

Participating Countries, Organizations, and Agencies:

North America:     Canada, USA, Mexico

Caribbean:             Antigua and Barbuda, Bahamas, Barbados, Belize, Dominica,

Grenada, Haiti, Guyana, Jamaica, Saint Lucia, Saint Vincent and the

Grenadines, Saint Christopher and Nevis, Suriname, Trinidad and Tobago

Central America:  Costa Rica, El Salvador, Guatemala, Honduras, Nicaragua, Panama,

Dominican Republic

Southern Cone:     Brazil, Bolivia, Chile, Paraguay, Uruguay

Andean:                 Colombia, Ecuador, Peru, Venezuela

SEP-Secretariat for Public Education of Mexico-serves as the general coordinator for project activities

UNESCO/OREALC-serves as the technical coordinator for the project

General Objective: To continue complying with the Summit of the Americas’ goals for educational success.  This project supports the construction of educational indicators based on the experience of international bodies in this subject.  It seeks to contribute in the search for effective educational policies in the region, strengthening the collection of data and information that allows for the construction of comparable indicators in the area of education, and to provide a prospective vision in analyzing the course to take.  It strives for an initiative that looks to contribute to international efforts intended to improve educational statistics systems for countries belonging to the Summit of the Americas by utilizing efforts and avoiding duplication which overburdens national technical teams and produces potential contradictory information.

Project Beneficiaries: Countries belonging to the Summit of Americas

Expected Results: Development and analysis of indicators: which countries arrange and make greater use of comparable indicators that report continuing to follow the Summit of Americas’ educational goals, which will be repetitious in the majority of processes for taking decisions.

Technical cooperation: Contribute to the strengthening of educational statistics systems for countries within the region through the use of tools and international rules and to contribute to the generation of a continuous process of strengthening statistics systems for countries within the region.

Diffusion and use of information: To account for periodic reports about progressing towards the achievement of the Summit of Americas’ educational goals, based on the use of comparable indicators.  Maintaining the PRIE website and contributing to the formation of an innovative culture and using evidence only in the making of decisions.

Context:

During the First Summit of Americas, the Heads of State compromised in undertaking the necessary actions to abolish educational obstacles that ruin social cohesiveness and hinder national prosperity, which is why this educational area has had special treatment.  In order to be at the forefront, it was observed that the usefulness of utilizing qualitative and quantitative measurements helps track advances in the subject.  For this reason, previous to the Second Summit of Americas, a Hemispheric Meeting of Ministers of Education was convened in which to agree upon a Plan of Action that was to be presented to the Heads of State for their respective approval.  All the same, the Plan recommended “establishing a system of common educational indicators which may allow for establishing comparisons at the hemispheric level.”  At the Second Summit of Americas (held in Santiago, Chile in April 1998), the central theme was “Education: The Key to Progress” was approved in the Plan of Action and it reiterated the advantageousness of establishing educational indicators for the improvement of national education systems.

As a result of the First Meeting of Ministers of Education, in success of the Inter-American Council for Integral Development (CIDI) of the OAS (held in Brasilia, 1998), the orchestration of a Regional Educational Indicators Project (PRIE) was agreed upon, coordinated by the Chilean Ministry of Education with the support for its design and execution by UNESCO.  The objectives of this project were focused on three fundamental areas: construction of indicators, technical cooperation and diffusion and analysis of their significance.  In August 2000, the countries approved a proposal for the execution of PRIE for a period of three years.  The results of this stated period of execution are found published in the volume “The Experience of the Regional Educational Indicators Project 2000-2003” and were presented before the Third Meeting of Ministers of Education of CIDI (held in Mexico, 2003).

During the Third Meeting of Ministers of Education of CIDI (held in Mexico, 2003), the countries decided to ask the Government of Mexico if it would assume coordination of a new phase of the Project.  The Mexican Government initiated this new phase of PRIE with a conviction in the goodness of the project in continuing to attain the marked goals within the mandates of the different Summits of Americas.  The same Heads of State from the Hemisphere, conscious of the importance of PRIE, in the Extraordinary Summit of Americas (held in Monterrey, Nuevo Leon, Mexico in January 2004), reiterated their promise to support this initiative, by including a specific paragraph in the “Declaration of Nuevo Leon.”

Project Justification:

One of the important tasks of these special areas is the support to ministerial meetings which meet periodically in the region as part of the process of the Summits of Americas.  These are found to promote dialogue and cooperation in specific sectors, as well as work, education, and sustainable development and to guarantee that Summit policies are implemented at the national level.  The OAS summons ministerial meetings, prepares abundant documents, and continues tracking implementation of Summit mandates, among other functions.  The ministers of education from the hemisphere met (in August in Tobago) to examine common challenges targeted for improving education quality in the member States.

The results of the activities developed in the project look for strengthening educational statistics within the framework of national statistical systems in light of the international promises made and provide to the Ministers necessary information for them to evaluate the improvements of member countries in the Summit of Americas and move them towards fulfilling the goals established for education within the mentioned framework.

Project Objectives:

PRIE was formed with the purpose of complying with the following objectives:

*constructing a basic set of comparable educational indicators for the Americas,

considering the existing initiatives

*strengthening national educational statistics systems in order to construct indicators and

develop a program for technical cooperation

*publish the indicators and promote their use in adoption of educational policies

Project Components:

With the purpose of obtaining these objectives, PRIE was conceived as a project composed of three components: construction and analysis of indicators, technical cooperation, diffusion and use of information to add to the general and technical coordination.

Component 1: Construction and analysis of educational indicators

Initially, the project will review the advances and results obtained for identifying new indicators to explore that may contribute to monitoring education quality in the member countries of the Summit of Americas.  In addition, the project anticipates proposing tasks to improve existing indicators and to approach definitions of indicators that may contribute to the discussion and to monitor education quality, responding to the demands of member countries in the Summit of Americas, in harmony with the specific project objectives.

In this way, the project seeks to respond to the Ministers’ needs for information by supporting discussions on country progress as they relate to the Summit goals and through elaboration of an educational indicators report about the general educational situation within member countries of the Summit of Americas.

The project should develop activities for supporting efforts that are being carried out across the hemisphere through concerted actions to measure academic successes from a comparable, international perspective.  These actions are not so much involved in evaluation of curriculum as they are in evaluation relative to criteria.  The incorporation of a large number of countries into the abovementioned regional/international initiatives is in a sense, one of the indicators that contribute in a substantial way to measurement of educational quality.  In this way, experiences, such as that of the UNESCO/OREALC Second Regional Comparative Study, among others, contribute to the generation of comparable information for monitoring education quality.

Component 2: Technical cooperation

The diagnostics developed by UNESCO were based on the Data Quality Assessment Framework to support PRIE.  These diagnostics allow for an integral look at countries’ education information systems by presenting key elements for the formulation of an integral program for technical cooperation.  These reports also form a valid tool in which to contribute to countries’ internal planning by paying attention to their needs and applicable program activities as an external element created by experts in the field.

The main purpose of this component is developing, apart from the detailed diagnostics, a set of specific actions in approaching common problems, which are just as much a part of national experiences as is the knowledge and technical norms provided by UNESCO.  With the available information in producing this proposal to date, an initial set of cooperative areas have been identified.  Although the final results from the diagnostics are in process, they are necessary to the effect of making improved accuracies and identify to countries a preliminary means as to how to direct their efforts.  Likewise, the development of actions in specific countries is subject to their expression of will and compromise on their part.

Component 3: Dissemination and use of information

The main purpose of this component is to respond to the information needs of the Ministers.  Through support of hemispheric meeting discussions and the publication and distribution of a report, assures that the information about the educational situation, within a set of relevant educational indicators, in countries belonging to the Summit of Americas is being used for developing comparable indicators.  In this way, the progress of the project is publicly accessible in a permanent manner.

Component 4: General and technical coordination

The main purpose of this component is coordinating the development of the project, including guiding the project politically and obtaining agreements relative to the goals and instrumentation of strategies consistent with the priorities and interest of the participating countries and the Summit goals through general coordination with the SEP-Secretariat for Public Education in Mexico and a Committee of Countries (Mexico, Trinidad and Tobago, El Salvador, Colombia, Chile, and Uruguay).  The Committee supports the country coordinator in managing and conducting project policy, as well as the participation of UNESCO as the cooperating organization responsible for the technical aspects of the project.

Description of Component Activities:

Component 1: Construction and analysis of educational indicators

Activity 1.1: Analyze curricular programs from non-Hispanic countries of the Caribbean in order to support the incorporation of a larger number of countries into the regional initiative SERCE-the Second Regional Comparative and Explanatory Study from the Latin American Laboratory for Evaluation conducted by OREALC/UNESCO in Santiago.

Activity 1.2: Review of an educational indicators report in 2006 about the general education situation in countries belonging to the Summit of Americas

Activity 1.3: Review of the report The Educational Panorama 2007 for the Ministerial Meeting commencing in 2007, focusing on the situation in countries surrounding the Summit of Americas’ goals

Component 2: Technical Cooperation

Activity 2.1: Meeting to take stock on the monitors involved in the diagnostic missions during 2005-2006 in order to detect common problems in developing a proper diagnostic tool

Activity 2.2: Carrying out of complementary diagnostics.  It is anticipated that between 8 to 10 requests for additional diagnostics in countries that were not visited in 2005-2006.

Activity 2.3: Developing 5 missions to countries for the purpose of producing and bringing up to date the plans for the international report

Activity 2.4: Apart from producing diagnostics in the region, developing a set of specific actions to tackle common problems is just as much a part of national experiences as is the knowledge and technical norms provided by UNESCO, with respect to: designing information systems; processing information; defining indicators for national systems; analysis and dissemination.  The activities correspond to five, three-day regional workshops with ten countries participating each year, according to the priority themes defined as part of carrying out diagnostics.

Activity 2.5: Participation in the Regional UNESCO (UIS and OREALC) Educational Statistics Workshop, corresponding to Latin America in 2007; supporting the specific project themes and contributing to the exchange and discussion of preponderant themes in the area of statistics and educational indicators, converting appropriate spaces for monitoring and setting in place common project advances and results.

Activity 2.6: Holding a workshop for Latin America, in cooperation with CEPAL, to discuss educational statistics provided from censuses and household surveys from a comparable, international, and intersectoral perspective and with participation from INES and other corresponding offices

Component 3: Dissemination and use of information

Activity 3.1: Production, publication, and distribution of a report relative to the activities of the period covering 2005-2007, a summary report of activities

Activity 3.2: Publication and dissemination of the report Educational Panorama 2007 for the Meeting of Ministers that will take place in 2007.  The meeting will be concerned with learning more about the advances towards completing the Summit goals.

Activity 3.3: Maintaining the PRIE website created containing PRIE activities and project documents

Activity 3.4: Publication and dissemination of the Caribbean curricular analysis report

Component 4: General and technical coordination

Activity 4.1: Two country committee meetings to continue carrying out the agreed upon actions and compromises, to provide more information about improvements, results, and successes obtained in the region and between countries, as well as discussing strategies for project implementation

Activity 4.2: Coordination, planning, continuation, and execution of technical work for PRIE that will be carried by UNESCO

Organizations Managing the Project:

SEP-Secretariat for Public Education of Mexico: general coordinator

Country Committee-Support the project’s coordination

OREALC/UNESCO Santiago: technical coordinator

Impact Evaluation:

*A short period of time for the project to present its objectives to the ministers and to the Summit countries and to analyze statistics using international educational information about the progress of countries towards achieving the Summit of Americas’ goals

*A long period of time for the project to strengthen the countries’ educational statistics systems, supporting technical cooperation in the area of systems design, generating information, defining indicators, disseminating and analyzing information

Results and Products:

*Caribbean curricular program analysis report

*2006 report on the state of education for the countries belonging to the Summit

*2007 report on the improvements that countries are making towards achieving the Summit goals for education

*Diagnostic documents for 8 to 10 countries and their respective educational statistics systems

*Report from the Regional Workshop and the 5 Technical Workshops carried during this period of time

*Monitors’ report from the meeting on the remaining activities left over

*PRIE activities report for the period of 2004-2007

*Maintaining and updating the PRIE website

Risk Evaluation:

*The principle challenges are guaranteeing the quality of information produced in responding to the difficulties of the ministers of education in terms of how far improvements have been made toward fulfilling the goals, which involves improving the collection and analysis of data.  Actions taking place within countries are necessary to be able to reach these objectives, such as evaluating the indicators produced and their systems for collecting and treating information.  What is more, actions taken from national institutions, such as establishing cooperation with other institutions that generate relevant educational information, principally with national institutes for statistics.

*The strategies to be placed for supporting these challenges are principally:

*Carrying out diagnostics for educational statistics systems in countries belonging to the Summit

*Technical support to countries in the design, generation, and dissemination of educational information

*Holding specific workshops that try to treat those questions, creating an atmosphere of technical cooperation, exchange of experiences and knowledge in the area of educational statistics

*Producing analytical reports and their dissemination concerning the education situation for the countries, principally, with respect to the improvements made towards fulfilling the Summit goals.

Contact Person for additional information:

Ana Maria Aceves Estrada,

General Director for Evaluation

Secretariat for Public Education of Mexico-SEP

Tele: (52-22)5705.7268

Fax: (52-55)5705.7001

Email: dgevalua@sep.gob.mx

Estimated Costs

| Component # | Activity | Contracts | Documents | Equipment | Others | Travel | Training | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1.1) Caribbean Curricular Analysis |  | 20,000 |  |  |  |  | 20,000 |
|  | 1.2) 2006 Indicators Report |  | 20,000 |  |  |  |  | 20,000 |
|  | 1.3) 2007 Panorama |  | 22,000 |  |  |  |  | 22,000 |
| 1 Total |  |  | 62,000 |  |  |  |  | 62,000 |
| 2 | 2.1) Workshop for monitors-balance of activities |  |  |  | 1,000 |  | 21,000 | 22,000 |
|  | 2.2) Diagnostics |  | 44,000 |  |  | 36,800 |  | 80,800 |
|  | 2.3) Plans to date |  | 13,750 |  |  |  | 9,500 | 23,250 |
|  | 2.4) Technical Workshops (5x10 countries) | 6,000 | 24,500 |  | 5,000 |  | 218,500 | 254,000 |
|  | 2.5) 2007 Workshop for Latin America |  |  |  | 2,000 |  | 75,600 | 77,600 |
|  | 2.6) Workshop for ministers & NSIs |  |  |  | 2,000 | 75,600 |  | 77,600 |
| 2 Total |  | 6,000 | 82,250 |  | 10,000 | 112,400 | 324,600 | 535,250 |
| 3 | 3.1) Printing & distributing 2005-2007 activities report |  | 12,000 |  | 2,500 |  |  | 14,500 |
|  | 3.2) Printing & distributing 2007 Panorama |  | 12,000 |  | 2,500 |  |  | 14,500 |
|  | 3.3) PRIE website maintenance |  |  |  | 14,800 |  |  | 14,800 |
|  | 3.4) Printing & distributing Caribbean curricular analysis |  | 4,000 |  | 1,500 |  |  | 5,500 |
| 3 Total |  |  | 28,000 |  | 21,300 |  |  | 49,300 |
| 4 | 4.1) Country Committee Meetings |  |  |  | 2,000 | 27,200 |  | 29,200 |
|  | 4.2) Technical coordination | 99,200 |  | 3,000 | 5,000 |  |  | 107,200 |
|  | 4.3) UNESCO overhead |  |  |  | 56,097 |  |  | 56,097 |
| 4 Total Grand Total |  | 99,200 105,200 | 172,250 | 3,000 3,000 | 63,097 94,397 | 27,200 139,600 | 324,600 | 192,497 839,047 |

Funds Requested

| Funds Requested from CIE | Funds Requested from SEP-Mexico | Other Funding-USAID |
| --- | --- | --- |
| 254,800 | 266,797 | 317,450 |