| Exercise | LE 1 |
| --- | --- |
| Category | Port Facility Live Exercise |
| Type | Access Control, Contiguous Zone, Contingency Response |
| Security Level | 1 or 2 |

## INTRODUCTION

- The security of a port facility depends not only on the careful planning and implementation of security measures, but also its’ response to incidents. Responses to security incidents should be pre-determined and specified in procedures in the PFSP. These incidents may not occur routinely but security staff needs to be ready to carry out the correct actions when they do occur.

- This live exercises allow port facility security personnel to carry out their duties in a controlled environment, thereby allow them to go through the decision making process to decide what actions to take and to take the correct actions according to procedures

## AIM

- To enhance the proficiency of the port facility security team in the control of access of personnel and material, monitoring of contiguous zones and contingency response.

## OBJECTIVES

- Security staff to handle routine security matter and contingencies with regards to access control and contiguous zone security in accordance with the procedures in the PFSP.

## DESIRED OUTCOMES

- On completion of the Exercise, the security team will be:

- Able to respond correctly to routine security matters and contingencies relating to access control, contiguous zone security.

- Able to carry out their duties relating to access control and contiguous zone confidently.

- Able to suggest changes or improvements to the security plan and procedures, if any.

## RESOURCES

Personnel

- Exercise Director : Mr XYZ (recommended to be senior designated person other than the PFSO)

- Planning Group – The Planning Group will not be necessary unless there is an intention to review or amend this exercise.  In this case, the following personnel are recommended:

- Security Manager or equivalent

- Operations Manager or equivalent

- Engineering Manager or equivalent

- Administration / Human Resources Manager or equivalent

- PSFO

- Ship Security Officer

- Controllers/Simulators:

- Chief Controller – Security Manager or equivalent

- Technical Controller – Engineering Supervisor or equivalent

- Simulator 1 – Assuming role of intruder – Should  NOT to be familiar to the players

- Simulator 2 – Driver of goods vehicle, should be known to the security staff, if possible.

- Simulators 3/4 – Assuming role of local residents. May have more if desired.

- 1 x driver of boat

- Crew for the boat, as required.

- Players:

- Port Facility Security Officer

- Security staff

- Operations staff

- Exercise Safety Officer – The appointment of one or more safety officers for this exercise should be considered.

Material

- Personnel and goods scanning equipment – to be in working condition

- Vehicles and stores

- Small boat.

- The Chief Controller should arrange with freight forwarders, suppliers or contractors for a consignment of cargo and a delivery vehicle to participate in this exercise.

- Props

- A simple invoice for a consignment of cargo showing an address in the port facility.

- Fishing gears for the boat crew and residents

- Communication

- For players – The existing communication infrastructure will be used.

- For Controllers – Mobile phone as preferred means with walkie-talkie as back up.

- Others

- Refreshment or meals – if required

- Controllers’ operations room with situation maps, list of injects and contact information of the participants

- Room for briefing and debriefing with computer, projector, screen and chairs

- Stationery for note taking

Budget

- Funding may be needed for the following:

- Employment of simulators and deliveryman

- Rental of vehicle and boat

- Refreshments.

- Reimbursement of expenses incurred by controllers or staff, if any.

## SCHEDULE OF EVENTS

- Refer to Exercise Announcement (or if there are changes, an updated schedule can be posted here)

## SCENARIO

- Port facility ABC has recently implemented ISPS and has put in place various measures to ensure the security of the port facility.  Previously, contractors, logistics companies as well as local residents used to enjoy unfettered access to the port facility.  As they are still not familiar with the new restrictions and requirements for access to the port facility, there have been frequent violations of the procedures, resulting in various conflicts.

## TASKS

- For Controllers:

- The crew on the small boat should stop the boat near to the port facility and will slowly creep / drift into the sea space controlled by the port facility.  The crew of the boat will cast their lines and pretend to fish. If the water around the port facility is a controlled area, the Chief Controller should arrange with the relevant authority for the boat to be granted access for the exercise.

- Initially, the driver of the vehicle with the consignment of cargo will attempt to enter the port facility without any documents. If asked for documents, he will say that he has left the documents in office and will take a few hours to go back to get the documents and will plead to go in without documentations.  On the second attempt, he will only have an invoice stating the delivery address which is located in the port facility and will again plea to be allowed to enter the port facility as he is already late and will be fired if he cannot deliver the goods.   He should try his best to persuade the security staff to let him enter the port facility.  Upon completion of this inject, he will show the necessary documentation and proceed to deliver the cargo.

- The intruder should only pretend to throw rocks and will coordinate with the technical controller to disable the CCTV camera.  The EPCT will choose the location of the CCTV camera.

- The group of “residents” will attempt to walk into the port facility without showing any forms of identification.  When asked, they will say that they are going to fish at the wharf and will insist on going there as they have used to in the past.

- The EPCT is free to alter or add any injects as required. Additional injects may be needed in response to the players’ reaction.

- The Safety Officers should follow the security staff as they carry out the exercise.

- For Players need to be familiar with the various procedures for granting access for personnel and cargo as well as contingency plans.

## TERMINATION

- The Chief Controller can terminate the exercise when it is deemed that the objectives have been achieved.

## MASTER EVENTS LIST

The flow of the live exercise is event based, as such, the timing is not critical. Expected response column is just a guide and should be substituted with existing standard operating procedure of port facility.

| S/N | Time | Event | Purpose | Action By | To | Means of Delivery | Expected response | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 001 | 0845 | All participants in position |  |  |  |  |  |  |
| 002 | 0900 | Exercise Start | Commence exercise | Chief Controller | All | Walkie Talkie | None |  |
| 003 | 0915 | Resident wants to enter the port facility to visit his friend. He did not have any forms of identification with him. | Test procedures for access control | Potential intruder | Guards at pass office | Walk to pass office | Follow procedures for granting access |  |
| 004 | 0920 | Small boat approach port facility | Test monitoring of seaward Contiguous Zone. | Boat skipper | Guards at security monitoring | Small boat | Detect, report and monitor location of boat |  |
| 005 | 0930 | Angry that he was not allowed in, vowed to create trouble for port facility | Follow up to inject, potential for further play | Potential intruder | Guards at pass office | Walk | Monitor, report |  |
| 006 | 0945 | Delivery driver attempts to deliver goods without documents. | Test procedures for cargo delivery | Delivery driver | Guards at goods entrance | Drive to port facility | Refuse entry |  |
| 007 | 0950 | The small boat stopped outside the restricted area of the port facility. | Follow up to inject | Boat skipper | Guards at security monitoring | Small boat | Report and monitor location of boat |  |
| 008 | 1005 | Man who was not allowed in, was seen throwing rock at CCTV cameras | Test monitoring of landward Contiguous Zone. | Potential intruder | Guards at security monitoring | Pretend to throw | Report, take actions to stop him. |  |
| 009 | 1010 | CCTV camera damaged | Response to equipment failure | Technical Controller | Guards at security monitoring | Disable CCTV | Report, repair, measures to maintain awareness (extra guards, etc) |  |
| 010 | 1020 | The small boat drifted inside Restricted Area | Test response to seaward intrusion | Boat skipper | Guards at security monitoring | Small boat | Intercept / warn boat |  |
| 011 | 1030 | Technician checking fault, need to replace camera, need about 1 hour | Follow up to inject | Technical Controller | Guards at security monitoring | Verbal | Arrangement to maintain awareness |  |
| 012 | 1040 | Delivery driver attempts to deliver goods with invoice. Says that he will be in trouble with the boss if he cannot deliver the goods and he is already late. | Follow up to inject. To test procedures for delivery of stores. | Delivery driver | Guards at goods entrance | Drive to port facility | Follow procedures for granting access |  |
| 013 | 1045 | Intrusion alarm. | Test responses to intrusion alarm. | Technical controller | Guards at security monitoring | Technician to trigger alarm remotely | Response to intrusion alarm. | False alarm |
| 014 | 1055 | The small boat departed Restricted Area | Close inject | Boat skipper | Guards at security monitoring | Small boat | Stand down |  |
| 015 | 1105 | A group of local residents (3-4) wants to enter the port facility to fish at the wharf. | Test procedures for personnel access | Residents | Guards at pass office | Walk | Security staff expected to follow procedures for granting access |  |
| 016 | 1115 | CCTV repaired | Close inject | Technical Controller | Guards at security monitoring | Enable CCTV | Verify proper function, stand down additional guards, etc |  |
| 017 | 1120 | Residents angry that they were not allowed in…Demands to see the boss. | Procedures for handling unrest. | Residents | Guards at pass office | Residents | Security staff expected to ask for assistance from PFSO. |  |
| 018 | When appropriate | Exercise End | End of exercise | Chief Controller | All | Walkie talkie | None |  |