THIRD REGULAR MEETING OF THE 		OEA/Ser.W/XIII.6.3

INTER-AMERICAN COMMITTEE ON EDUCATION				CIDI/CIE/INF. 5/06

October 26 – 27, 2006				19 October 2006

Washington, D. C. 								Original: English

PRELIMINARY DRAFT WORK PLAN 2007 – 2010

“INTER-AMERICAN PROGRAM ON EDUCATION FOR DEMOCRATIC VALUES AND PRACTICES”

## Proposed Work Plan 2007-2010

Inter-American Program on Education for Democratic Values and Practices

The Inter-American Democratic Charter of the Organization of American States emphasizes the important role played by education in developing and sustaining a culture of democracy in the countries of the Americas. In August 2005, the Ministers of Education of the hemisphere committed themselves to adopting a hemisphere-wide program of education for democratic values and practices -- the culmination of a broad range of activities undertaken within the framework of the OAS to strengthen democracy through education.  The Program would have three mutually reinforcing components:/

- Research component

- Professional development and educational resource component

- Information exchange component.

Ministers asked the Inter-American Education Committee (CIE) to facilitate the development of a detailed and feasible work plan, benchmarks for progress, a proposed budget and sources of financing for the program’s first phase.

Ministers further specified that these items should be developed by “a working group of interested member countries led by Colombia, with assistance from the Department of Education and Culture (DEC) of the OAS in collaboration with the Department for Governance, and with guidance from an Advisory Group composed of citizenship education officials from member states, academic and civil society experts, and other appropriate, interested partners. The work plan, including specific initial activities and proposed sources of financing, should be presented to the CIE executive committee and authorities, before the end of this year.  Among the initial activities in the work plan, to hold, in Mexico in the first quarter of 2006, a meeting of representatives of member states on successful experiences in citizenship education.” (CIDI/RME/doc.13/05 rev. 2)  The Ministers also requested that the CIE report on progress in implementing the Program at the V Meeting of Ministers of Education in 2007.

In response to this mandate the Authorities and Executive Committee of the CIE supported the first phase of the Inter American Program. This phase included inviting countries to form part of a coordinating group, the first meeting of the Advisory Board for the Inter American Program held April 17-19, 2006 in Bogotá, Colombia, the development of a Web Portal for the Program launched in June 2006, a mapping of current policies and programs in the hemisphere in education for democratic citizenship in process, and the organization of an International Seminar on Best Practices in Citizenship Education held July 2006 in Mexico City. (See progress report of the Inter American Program for a summary of results and outcomes).

The Department of Education and Culture, in collaboration with the Ministry of National Education of Colombia has developed the following proposal for a 2007-2010 work plan with concrete activities in each of the three components of the Program and with estimated costs and dates of execution. A timeline with benchmarks is also included.  The suggested activities are based on specific recommendations provided by the Advisory Board at their first meeting in Bogotá, Colombia in April 2006. (See recommendation in annex 2).

This is a preliminary proposal for discussion that covers a wide range of activities to be funded by a wide range of partners. The comments of the member states will be incorporated into a final proposal to be presented to the CIE Authorities and other potential donors.

Summary of proposed activities by component, 2007-2010

Research Component:

- Inter American Journal of Education for Democracy

- Inventory of existing research and research institutions in citizenship education and related areas the hemisphere

- State of the art on evaluation and assessment of programs and policies in education for democratic citizenship

- Publication on priority topic identified by Advisory Board

Professional Development and Educational Resources Component:

- Regional Distance Course for Teachers: The Inter American Democratic Charter and the Teaching of Democratic Values and Practices (Spanish Version)

- Education for Democratic Citizenship in the Caribbean: An distance course for educators

- Publication on teaching democratic values and practices

- Video and media series on democratic pedagogy (developing proposal)

- Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal)

Information Exchange Component:

- Web Portal, On-line Bulletin, and Brochure

- Portfolio of Promising Initiatives and Policy Brief Series

- Advisory Board meetings

- Information exchange workshops on policies and practices (2 per year)

Monitoring and Evaluation of Program 2007-2010

Description of activities for Phase 11:

#### Research Component

Activity 1:  Inter American Journal of Education for Democracy

Description:  The Inter American Journal on Education for Democracy forms part of the research component of the Inter American Program.  The objective of the journal is to promote quality research in the Americas on education for democratic citizenship. The development of the journal is guided by the following specific recommendations of the Advisory Board a) support new research, including cross-sectional and longitudinal studies b) facilitate and encourage the use of a variety of research approaches and methodologies c) monitor and provide periodic incentives or recognition to research experiences developed within educational centers (schools, universities, etc.) or by members of the educative community (teachers, students, parents, etc) and c) promote the creation of a citizenship education research network (including universities, research centers and individual researchers.)

The journal will be published twice a year and on-line by the OAS in collaboration with the University of Indiana, University of Toronto, Catholic University of Chile, and the Center for Civic Education and other interested partners.  The journal will have an editorial board with balanced representation from key scholars in the field from around the Americas.

- Estimated date of execution: November 2006  to November 2010

- Total estimated costs of the activity per object of expenditure (in US $):

Per year: $35,000 (on-line)

- 10,000	journal administration and coordination

- 10,000	editorial costs

- 10,000	journal design / programming / web page

- 5,000	other costs (dissemination, communications)

Four years: $140,000 4 yrs (on-line) Additional costs for printed publication not included.

Activity 2: Inventory of existing research and research institutions in the hemisphere

Description: Advisory Board members recommended that the OAS do an inventory of existing research and institutions that are working on investigating different aspects of education for democratic citizenship. This inventory will help identify the gaps that exist in research and will provide an important resource for students, teachers, practitioners, and policymakers interested in research findings on OAS member states.  The research compiled will adhere to specific guidelines outlined by the Advisory Board members in annex 2. The research will be made available to the public through a database that is currently available on the Inter American Program’s Web Portal. Select research will be highlighted in the Inter American Journal on Education for Democracy and through the Program’s On-line bulletin.

- Estimated date of execution: January-December 2007 and January-December 2009

- Total estimated cost of the activity per object of expenditure (in US $):

Per year: $ 10,000

- Contract ( 10,000 CPR)

Two years: $ 20,000 2007, 2009

Activity 3: State of the Art on Evaluation and Assessment of Programs and Policies in Education for Democratic Citizenship (Jan-Dec 2007) /

Description:  Among the clear gaps identified by Advisory Board members is the lack of information on current efforts to monitor and evaluate the impact of policies and programs in education for citizenship in the Americas.

With the support of a grant from the Government of Colombia, the Program will commission a report on the current state of evaluation of policies and programs in this area. In line with the specific recommendations of the Advisory Board, the report will highlight different approaches and methodologies used for both formative and summative evaluations of policies and programs in democratic citizenship education.

The results of the commissioned report will be presented at an international meeting on evaluation of policies and programs in democratic citizenship education to be hosted by the Department of Education and Culture in October or November of 2007 with participation from OAS member states, universities, and civil society organizations working in the field from around the Americas. (See component 3)

- Estimated date of execution: January2007-October 2007

- Total estimated cost of the activity per object of expenditure (in US $):

1 year: $15,000

  - Document design/reproduction ($5,000)

  - Contract ($10,000 CPR)

  - Other expenses (communications, office space, etc.)

Activity 4:  Publication on priority topic identified by the Advisory Board

Description:  In the research component, Advisory Board members recommended that the OAS commission a state of the art document on research in citizenship education during at least the last five years and widely disseminate the document.  Advisory Board Members also made recommendations on potential research topics such as research on policy mandates and policy implementation; impact of other factors beyond the school, such as parents, the media, the NGOs, community leaders; educational governance such as student governments, voting and other indicators of civic health; gaps in the application of citizenship education in different settings such as high poverty contexts or high conflict contexts; connection of citizenship education to other areas of education, such as human rights education or peace education, even environmental educational.(see final report from the Advisory Board Meeting at www.educadem.oas.org for a complete list of recommended research topics)

- Estimated date of execution: June 2007-December 2009

- Total estimated cost of the activity per object of expenditure (in US $):

- Per Year: $43,333  (average expenditure)

Three years: $130,000 (estimate costs based on 2005 OAS study)

  - Document design/reproduction ( $30,000)

  - Contracts ($50,000)

  - Travel $25,000 ($12,500 per planning meeting in Washington DC with key experts and project consultants)

  - Other (communications, dissemination, etc.) ($25,000)

#### Professional Development and Educational Resources Component

Activity 1:  Distance Course in teaching democratic values and practices in Spanish

Description:  Advisory Board members recommended that the OAS a) facilitate meetings among teachers for the exchange of practices in courses that favor democratic values in living together in the school b) offer countries of the region a resource bank in order to facilitate professional development c) offer countries of the regions contents, methodologies, and resources (videos, publications, CDs, etc.) for the training of student leaders who can appropriate and disseminate democratic values. In addition they recommended that OAS member states favor the incorporation of formation in democratic values in the national plans of pre and in-service teacher training.

In line with these recommendations the OAS and its partners have developed and begun implementing a pilot project to train teachers in democratic values and practices in Peru over the past year. This project has been provided generous support by the US Mission to the OAS. The project seeks to provide primary and secondary teachers with knowledge and tools and resources for creating democratic classrooms. The lessons learned from this pilot will be incorporated into the final versions of the course offered to all interested member states of the OAS. The lessons also are being provided to policy makers through the Ministerial and CIE Processes and other opportunities/venues. The proposal is under development and these figures are estimates.

- Estimated date of execution: January 2006-2010

- Total estimated cost of the activity per object of expenditure (in US $):

Per year: $125,000 U.S.

    - Training: $50,000

    - Travel: $10,000

    - Document: $5,000

    - Equipment: $5,000

    - Contracts: $30,000

    - Others: $25,000

Four Years:  $500,000 U.S.

Activity 2:  Education for democratic citizenship in the Caribbean: A distance course for educators in English

Description: This project aims to strengthen teaching practices at the classroom level so that teachers and students become more democratic and reflective. The project will accomplish this goal by developing an on-line multimedia system for distance education which among its principal elements includes:

- A virtual classroom in which the students will find the tools for information, communication, learning and evaluation.

- On-line and “real” tutors.

- Support and reading material

- Printed material, videos or discs may also be used either to complement the contents of the course, or to disseminate it in remote regions

- Network of teacher trainers and teachers implementing democratic classrooms.

This course, which builds on the existing experience of the Peru pilot project described above, forms part of the Professional Development and Educational Resources Component of the Inter-American Program on Education for Democratic Values and Practices.

In addition to the 75 hour distance courses in Peru and the Caribbean the project will produce a 25 hour stand-alone on-line course on democracy in the Americas that will be available to all member states and interested parties.

- Estimated date of execution: 2007-2009

- Total cost of the activity per object of expenditure (in US $):

Per Year: $190,000

    - Training: $70,000

    - Travel: $25,000

    - Document: $10,000

    - Equipment: $15,000

    - Contracts: $50,000

    - Others: $20,000

Three Years: $570,000

Activity 3. Publication for teachers on democratic classrooms

Description:  In the Professional Development component, Advisory Board members recommended that the Program offer teachers and trainers of the region contents, methodologies, and resources (videos, publications, CDs, etc.).   Currently, the OAS is involved in three major teacher networks that include UNESCO’s KIPUS Teacher’s Network, PREAL’s working group on teachers, and the OAS Inter-American Teacher Educator Network. All three cover different regions and have different thematic focuses. However, all three portend to have as a primary objective changing classroom practice to improve student learning.  This publication would focus on leveraging the comparative advantages and experiences of each network in order to produce a joint publication on teaching democratic values and practices.

- Estimated date of execution: June 2008-December 2010

- Total estimated cost of the activity per object of expenditure (in US $):

- Per Year: $43,333  (average expenditure)

Three years: $130,000 (estimate costs based on 2005 OAS study)

  - Document design/reproduction ($30,000)

  - Contracts ($50,000)

  - Travel $25,000 ($12,500 per planning meeting in Washington DC with key experts and project consultants)

  - Other (communications, dissemination, etc.) ($25,000)

Activity 4:  Video and media series on democratic pedagogy (currently developing proposal / budget and timeline not included here)

Description: With Professional Development, the Program’s Advisory Board recommended that the OAS develop activities that facilitate reflection of professional practice (self observation, team or expert observation) as well as transformation of professional practice through an analysis of documented experiences.  In response the Department of Education and Culture proposes developing an initiative in collaboration with the Information Exchange working group of the Inter American Program that aims to produce a series of videos on democratic pedagogies and schools. The project could consider taking advantage of the current implementation of democratic classrooms in both the Caribbean and Peruvian Pilot projects.

(Costs to be determined)

Activity 5:  Promoting Tolerance and Diversity in the Americas: Radio and video series (currently developing proposal / budget and timeline not included here)

Description: The Department for the Promotion of Governance is currently developing a program proposal focusing on advocacy about tolerance and diversity in the hemisphere. The initiative will develop a series for radio and video programs with in-depth interviews on issues related to diversity, tolerance, and other democratic values. In its first series the project will focus on the experience of afro-descendents in the Americas.  The broadcasts will be available through the Web Portal of the Inter American Program and the Voice of the OAS Radio Series.

(Costs to be determined)

#### Information Exchange Component

Activity 1:  Inter American Program web portal, on-line bulletin, and brochure

Description:  In the Information Exchange Component Advisory Board members recommended that the OAS develop mechanisms in order to facilitate networking and the sharing of products, resources, research summaries, information on policies, professional development and emerging issues. In addition, the advisory Board recommended that the OAS disseminate information to policy makers, education leaders and other stakeholders.

In line with these recommendations the OAS has developed the web portal for the Inter-American Program at www.educadem.oas.org  .  This on-line site contains research findings, programs, projects, resources, and events in the hemisphere for different actors working in the field of education for democracy. The site also has links to other web pages from ministries of education, the Network of Portals and other non-governmental and international organizations in the area of education for democracy.  One of the main features of the website is its interactive multimedia features that include on-line forums, on-line distance education courses in education for democracy, research databases, and an on-line bulletin that focuses on different key issues in education for democracy. The bulletin is published three times a year and the first bulletin is now available on the web portal and the second bulletin will be published in November 2006. (see www.educadem.oas.org )

The OAS will design and print a brochure to explain and promote the Inter-American Program.

- Estimated date of execution: January 2007-December 2010

- Total cost of the activity per object of expenditure (in US $):

Per year:	$8,300 (average expenditure)

- Contracts: $7200 Web Portal maintenance, programming, and host fees + $2400 programming 3 on-line bulletins + $2000 (initial design of brochure)

- Others: $2400 printing brochure

Four years:	$33,200

Activity 2:  Portfolio of Promising Initiatives, Databases, On-line Bulletin, and Policy Briefs

Description:  In the Information Exchange Component, Advisory Board members recommended that the OAS disseminate information regarding the Program and its three components to policy makers, education leaders and other stakeholders. The Program would identify and hire an expert in citizenship education that would be responsible for developing various products of the Information Exchange component that aim to disseminate information on the Program to different stakeholders. Principle activities would include:

- Update the portfolio of promising initiatives. In addition to surveying the countries, a citizenship education specialist would continue to populate the research and policy and programs databases that are available on the Web Portal at www.educadem.oas.org

- Develop contents for the on-line bulletin. The Program is producing approximately 3 on-line bulletins per year on different key issues in education for democracy. The first bulletin is now available on the web portal and the second bulletin will be published in November 2006. (see www.educadem.oas.org)

- Develop 3 policy briefs per year on key research findings for policymakers.  Each policy brief will focus on key themes and be presented in a language and style that is useful for policy-makers and educational leaders engaged in developing, implementing, or evaluating citizenship education reforms.

- Estimated date of execution: January 2007-December 2010

- Costo total de la actividad por el objeto del gasto (En US$):

Per Year: $35,000 (Contract CPR)

Four Years: $140,000

Activity 3:  Advisory Board Meetings 2008 and 2010

Description: In the Commitments to Action from Scarborough, ministers asked the Inter-American Committee on Education (CIE) to launch the Inter-American Program by facilitating the development of a detailed work plan, benchmarks, and proposals for funding the first stage of the program. In addition, the ministers asked that these components be developed by a coordinating group of interested member countries with guidance from an Advisory Board that should include officials from member states, educational institution personnel, and experts from civil society and other groups working in the field.  In order to support this process the technical secretariat of the CIE facilitated the identification and selection of Advisory Board members from throughout the member states and organized their first meeting in Bogotá, Colombia on April 19-21, 2006 with financial support from the Ministry of Education of Colombia, the Inter-American Committee on Education, and the Center for Civic Education. The main purpose of the meeting was to produce concrete recommendations and suggestions to be used in the design of the work plan of the Inter-American Program.  The Advisory Board will continue to play an important role in the development and monitoring of the Program by helping to identify gaps in knowledge and resources in each of the three areas of the Program. In addition to identifying the gaps the Advisory Board will play a key role in the identification of key partners and resources that can support the Program’s activities.

- Estimated date of execution:  April 2008 and April 2010

- Total cost of the activity per object of expenditure (in US $):

Per Year:     $71,000

  - Travel: 50,000

  - Doc. 6,000

  - Equip: 2,000

  - Contracts: 5,000

  - Others: 8,000 (Interpretation: 6,000 and misc. 2,000)

Two Years: $142,000

Activity 4:  2 yearly Horizontal Cooperation Workshops on policies and practices in education for democratic citizenship

Description: At the III and IV Meeting of the Ministers of Education, member countries requested that the OAS continue to promote horizontal cooperation workshops in order to share the lessons learned from implementing policies and programs in key priority areas including education for democracy. In addition, Advisory Board members recommended that the OAS favor opportunities for meeting and exchange among the Program’s protagonists within the information exchange component.  In July 2006 Mexico offered the first workshop within the framework of the Program’s Information Exchange component (see http://www.educadem.oas.org/mexico/ingles/fr_welcome.html).  The Program will organize two knowledge sharing workshops per year in different host countries.  The following two workshops are planned for 2007:

Workshop 1: The Inter American Program will partner with the Global Issues Resource Center, UNDP, the United States Institute of Peace, the Ohio Department of Education, Ohio Department of Health, Temple University, Ohio Resource Network, Interfaith Center for Peace, Hispanic Council, Ohio Commission on Dispute Resolution and Conflict Management, Maryland Mediation and Conflict Resolution Office to host a four-day Inter-American Summit on Conflict Resolution Education in Cleveland, Ohio from March 14-17, 2007.  The Summit will bring together government representatives from among the 50 states in the U.S. and 34 countries of the Americas and their non-governmental organization partners who have legislation or policies in place to deliver conflict resolution education at the K-12 level and in colleges of teacher education.  Participants will exchange program best practices, evaluation methodology, creation of policy implementation structures, and consideration of obstacles to success.

Workshop 2: Among the clear gaps identified by Advisory Board members is the lack of information on current efforts to monitor and evaluate the impact of policies and programs in education for citizenship in the Americas. With the help from a grant from the Government of Colombia the Program will commission a report on the current status of evaluation of policies and programs in this area. In line with the specific recommendations of the Advisory Board, the report will highlight different approaches and methodologies used for both formative and summative evaluations of policies and programs in democratic citizenship education.  The results of the commissioned report will be presented at this international meeting on evaluation of policies and programs in democratic citizenship education to be hosted by the Department of Education and Culture in October or November of 2007 with participation from OAS member states, universities, and civil society organizations working in the field from around the Americas.

- Estimated date of execution:  2007 -2010

- Total cost of the activity per object of expenditure (in US $):

Four Years: $ 560,000

Per Year: $140,000 (70,000 per workshop)

  - Travel: 50,000 x 2 = 100,000

  - Doc. 5,000 x 2 = 10,000

  - Equip: 5,000 x 2 = 10,000

  - Others: 10,000 x 2 = 20,000 (Interpretation, room fees, etc.)

Monitoring and Evaluation 2007-2010

Description: Each activity will incorporate, from its inception, a plan for the evaluation of its implementation and results.  In addition, the overall Program will incorporate: (a) biannual reports submitted by the General Secretariat to the Inter-American Committee on Education and to the Permanent Council; (b) evaluations completed by the participants in each program activity; and (c) a periodic external evaluation of the overall outcomes of the program./ The Periodic external evaluation will be done towards the end of 2008 and at the end of 2010.

Estimated date of execution: 2007-2010

Total cost of the activity per object of expenditure (in US $):

2007 Monitoring

- Contracts: $10,000

2008 Monitoring and Formative Evaluation

- Travel: $10,000

- Doc: $500

- Contracts: $ 30,000

- Other: $2,000

2009 Monitoring

- Contracts: $10,000

2010 Monitoring and Summative Evaluation

- Travel: $15,000

- Doc: $5,000

- Contracts: $30,000

- Other: $5,000

Total Estimated Costs and Fund Requests Per Year:

| Budget Year 2007 | Estimated costs by activity |  |  |  | Requests for funding by activity |
| --- | --- | --- | --- | --- | --- |
|  | Months | Training | Travel | Doc. | Equipment | Contracts | Others |  | TOTALS |  | Request | OAS request | Country request | Donor request |
| Component | Weeks | 3 | 4 | 5 | 6 | 8 | 9 |  |  |  | CIE | Counterpart | Counterpart | counterpart |
| Research Component | Act. 1 Inter American Journal |  |  |  |  | $10,000 | $25,000 |  | $35,000 |  | $0 | 10,000 |  | $25,000 |
|  | Act. 2 Inventory of existing research and research institutions |  |  |  |  | $10,000 |  |  | $10,000 |  | $10,000 |  |  |  |
|  | Act. 3 State of the art on evaluation and assessment of programs and policies |  |  | $5,000 |  | $10,000 |  |  | $15,000 |  | $5,000 |  | $10,000 |  |
|  | Act. 4 Publication on priority topic identified by Advisory Board |  | $25,000 | $30,000 |  | $50,000 | $25,000 |  | $130,000 |  |  |  |  | $130,000 |
| Professional Development and Educational Resources | Act 1. Regional Distance Course for Teachers: (Spanish Version) | $50,000 | $10,000 | $5,000 | $5,000 | $30,000 | $25,000 |  | $125,000 |  |  | $15,000 | $20,000 | $90,000 |
|  | Act 2. Education for Democratic Citizenship in the Caribbean: A distance course for educators | $70,000 | $25,000 | $10,000 | $15,000 | $50,000 | $20,000 |  | $190,000 |  |  | $20,000 | $40,000 | $130,000 |
|  | Act. 3 Publication on teaching democratic values and practices |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act. 4 Video and media series on democratic pedagogy (developing proposal) |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act 5. Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal) |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
| Information Exchange | Act. 1 Inter American Program web portal, on-line bulletin, brochure, Policy Briefs |  |  |  |  | $9,200 | $2,400 |  | $11,600 |  | $11,600 |  |  |  |
|  | Act 2. Portfolio of Promising Initiatives |  |  |  |  | $35,000 |  |  | $35,000 |  | $35,000 |  |  |  |
|  | Act 3. Advisory Board meetings |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act. 5 Two Information exchange workshops on policies and practices |  | $100,000 | $10,000 | $10,000 |  | $20,000 |  | $140,000 |  | $50,000 | $50,000 | $20,000 | $20,000 |
| Monitoring and Evaluation |  |  |  |  | $10,000 |  |  | $10,000 |  |  |  |  | $10,000 |
| Totals: |  | $120,000 | $160,000 | $60,000 | $30,000 | $214,000 | $117,400 |  | $701,600 |  | $111,600 | $95,000 | $90,000 | $405,000 |

| Budget Year 2008 | Estimated costs by activity |  |  |  | Requests for funding by activity |
| --- | --- | --- | --- | --- | --- |
|  | Months | Training | Travel | Doc. | Equipment | Contracts | Others |  | TOTALS |  | Request | OAS request | Country request | Donor request |
| Component | Weeks | 3 | 4 | 5 | 6 | 8 | 9 |  |  |  | CIE | Counterpart | Counterpart | counterpart |
| Research Component | Act. 1 Inter American Journal |  |  |  |  | $10,000 | $25,000 |  | $35,000 |  | $0 | $10,000 |  | $25,000 |
|  | Act. 2 Inventory of existing research and research institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 State of the art on evaluation and assessment of programs and policies |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Publication on priority topic identified by Advisory Board |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Professional Development and Educational Resources | Act 1. Regional Distance Course for Teachers: (Spanish) | $50,000 | $10,000 | $5,000 | $5,000 | $30,000 | $25,000 |  | $125,000 |  |  | $15,000 | $20,000 | $90,000 |
|  | Act 2. Education for Democratic Citizenship in the Caribbean: A distance course for educators | $70,000 | $25,000 | $10,000 | $15,000 | $50,000 | $20,000 |  | $190,000 |  |  | $20,000 | $40,000 | $130,000 |
|  | Act. 3 Publication on teaching democratic values and practices |  | $25,000 | $30,000 |  | $50,000 | $25,000 |  | $130,000 |  |  |  |  | $130,000 |
|  | Act. 4 Video and media series on democratic pedagogy (developing proposal) |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act 5. Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal) |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
| Information Exchange | Act. 1 Inter American Program web portal, on-line bulletin, and brochure |  |  |  |  | $7,200 |  |  | $7,200 |  | $7,200 |  |  |  |
|  | Act 2. Portfolio of Promising Initiatives |  |  |  |  | $35,000 |  |  | $35,000 |  | $35,000 |  |  |  |
|  | Act 3. Advisory Board meetings |  | $50,000 | $6,000 | $2,000 | $5,000 | $8,000 |  | $71,000 |  | $36,000 | $30,000 | $5,000 |  |
|  | Act. 4 Two Information exchange workshops on policies and practices |  | $100,000 | $10,000 | $10,000 |  | $20,000 |  | $140,000 |  | $50,000 | $50,000 | $20,000 | $20,000 |
| Monitoring and Evaluation |  | $10,000 | $500 |  | $30,000 | $2000 |  | $42,500 |  |  |  |  | $42,500 |
| Totals: |  | $120,000 | $220,000 | $61,500 | $32,000 | $217,200 | $125,000 |  | $775,700 |  | $128,200 | $125,000 | $85,000 | $437,500 |

| Budget Year 2009 | Estimated costs by activity |  |  |  | Requests for funding by activity |
| --- | --- | --- | --- | --- | --- |
|  | Months | Training | Travel | Doc. | Equipment | Contracts | Others |  | TOTALS |  | Request | OAS request | Country request | Donor request |
| Component | Weeks | 3 | 4 | 5 | 6 | 8 | 9 |  |  |  | CIE | Counterpart | Counterpart | counterpart |
| Research Component | Act. 1 Inter American Journal |  |  |  |  | $10,000 | $25,000 |  | $35,000 |  | $0 | $10,000 |  | $25,000 |
|  | Act. 2 Inventory of existing research and research institutions |  |  |  |  | $10,000 |  |  | $10,000 |  | $10,000 |  |  |  |
|  | Act. 3 State of the art on evaluation and assessment of programs and policies |  |  | $5,000 |  | $10,000 |  |  | $15,000 |  | $5,000 |  | $10,000 |  |
|  | Act. 4 Publication on priority topic identified by Advisory Board |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Professional Development and Educational Resources | Act 1. Regional Distance Course for Teachers: (Spanish) | $50,000 | $10,000 | $5,000 | $5,000 | $30,000 | $25,000 |  | $125,000 |  |  | $15,000 | $20,000 | $90,000 |
|  | Act 2. Education for Democratic Citizenship in the Caribbean: A distance course for educators | $70,000 | $25,000 | $10,000 | $15,000 | $50,000 | $20,000 |  | $190,000 |  |  | $20,000 | $40,000 | $130,000 |
|  | Act. 3 Publication on teaching democratic values and practices |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act. 4 Video and media series on democratic pedagogy (developing proposal) |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act 5. Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal) |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
| Information Exchange | Act. 1 Inter American Program web portal, on-line bulletin, and brochure |  |  |  |  | $7,200 |  |  | $7,200 |  | $7,200 |  |  |  |
|  | Act 2. Portfolio of Promising Initiatives |  |  |  |  | $35,000 |  |  | $35,000 |  | $35,000 |  |  |  |
|  | Act 3. Advisory Board meetings |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act. 4 Two Information exchange workshops on policies and practices |  | $100,000 | $10,000 | $10,000 |  | $20,000 |  | $140,000 |  | $50,000 | $50,000 | $20,000 | $20,000 |
| Monitoring and Evaluation |  |  |  |  | $10,000 |  |  | $10,000 |  |  |  |  | $10,000 |
| Totals: |  | $120,000 | $135,000 | $30,000 | $30,000 | $162200 | $90,000 |  | $567,200 |  | $107,200 | $95,000 | $90,000 | $275,000 |

| Budget Year 2010 | Estimated costs by activity |  |  |  | Requests for funding by activity |
| --- | --- | --- | --- | --- | --- |
|  | Months | Training | Travel | Doc. | Equipment | Contracts | Others |  | TOTALS |  | Request | OAS request | Country request | Donor request |
| Component | Weeks | 3 | 4 | 5 | 6 | 8 | 9 |  |  |  | CIE | Counterpart | Counterpart | counterpart |
| Research Component | Act. 1 Inter American Journal |  |  |  |  | $10,000 | $25,000 |  | $35,000 |  | $0 | $10,000 |  | $25,000 |
|  | Act. 2 Inventory of existing research and research institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 State of the art on evaluation and assessment of programs and policies |  |  | $5,000 |  | $10,000 |  |  | $15,000 |  | $5,000 |  | $10,000 |  |
|  | Act. 4 Publication on priority topic identified by Advisory Board |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Professional Development and Educational Resources | Act 1. Regional Distance Course for Teachers: (Spanish) | $50,000 | $10,000 | $5,000 | $5,000 | $30,000 | $25,000 |  | $125,000 |  |  | $15,000 | $20,000 | $90,000 |
|  | Act 2. Education for Democratic Citizenship in the Caribbean: A distance course for educators |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 Publication on teaching democratic values and practices |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act. 4 Video and media series on democratic pedagogy (developing proposal) |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
|  | Act 5. Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal) |  |  |  |  |  |  |  | $0 |  |  |  |  |  |
| Information Exchange | Act. 1 Inter American Program web portal, on-line bulletin, and brochure |  |  |  |  | $7,200 |  |  | $7,200 |  | $7,200 |  |  |  |
|  | Act 2. Portfolio of Promising Initiatives |  |  |  |  | $35,000 |  |  | $35,000 |  | $35,000 |  |  |  |
|  | Act 3. Advisory Board meetings |  | 50,000 | $6,000 | $2,000 | $5,000 | $8,000 |  | $71,000 |  | $36,000 | $30,000 | $5,000 |  |
|  | Act. 4 Two Information exchange workshops on policies and practices |  | $100,000 | $10,000 | $10,000 |  | $20,000 |  | $140,000 |  | $50,000 | $50,000 | $20,000 | $20,000 |
| Monitoring and Evaluation |  | $15,000 | $5,000 |  | $30,000 | $5,000 |  | $55,000 |  |  |  |  | $55,000 |
| Totals: |  | $50,000 | $175,000 | $31,000 | $17,000 | 127,200 | $83000 |  | $483,200 |  | $133,200 | $105,000 | $55,000 | $190,000 |

| Total Estimate 4 years | Estimated costs by Year |  |  |  | Requests for funding by Donor |
| --- | --- | --- | --- | --- | --- |
|  |  | Training | Travel | Doc. | Equipment | Contracts | Others |  | TOTALS |  | Request | OAS | Country | Donor |
|  |  | 3 | 4 | 5 | 6 | 8 | 9 |  |  |  | CIE | Counterpart | Counterpart | counterpart |
|  | Years |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Totals: | 2007 | $120,000 | $160,000 | $60,000 | $30,000 | $214,000 | $117,400 |  | $701,600 |  | $111,600 | $95,000 | $90,000 | $405,000 |
| Totals: | 2008 | $120,000 | $220,000 | $61,500 | $32,000 | $217,200 | $125,000 |  | $775,700 |  | $128,200 | $125,000 | $85,000 | $437,500 |
| Totals: | 2009 | $120,000 | $135,000 | $30,000 | $30,000 | $162200 | $90,000 |  | $567,200 |  | $107,200 | $95,000 | $90,000 | $275,000 |
| Totals: | 2010 | $50,000 | $175,000 | $31,000 | $17,000 | 127,200 | $83000 |  | $483,200 |  | $133,200 | $105,000 | $55,000 | $190,000 |
| Sub Totals: | 2007-2010 | $410,000 | $690,000 | $182,500 | $109,000 | $720,600 | $415,400 |  | $2,527,700 |  | $480,200 | $420,000 | $320,000 | $1,307,500 |
|  | Overhead 8% (included in each activity budget) |  |  |  |  |  |  | $202,216 |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Total Request CIE | $480,200 |  |  |  |

Total Estimated Costs and Fund Requests 2007-2010

|  | Months | 2007 |
| --- | --- | --- |
| Component | Weeks |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Jan | Feb | Mar | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec |
| Research Component | Act. 1 Inter American Journal |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 2 Inventory of existing research and research institutions |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 State of the art on evaluation and assessment of programs and policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Publication on priority topic identified by Advisory Board |  |  |  |  |  |  |  |  |  |  |  |  |
| Professional Development and Educational Resources | Act 1. Regional Distance Course for Teachers: Spanish Version |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 2. Education for Democratic Citizenship in the Caribbean: A distance course for educators |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 Publication on teaching democratic values and practices |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Video and media series on democratic pedagogy (developing proposal) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 5. Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal) |  |  |  |  |  |  |  |  |  |  |  |  |
| Information Exchange | Act. 1 web portal, on-line bulletin, and brochure |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 2. Portfolio of Promising Initiatives |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 3. Advisory Board meetings |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Two Information exchange workshops on policies and practices |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Months | 2008 |
| --- | --- | --- |
| Component | Weeks |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Jan | Feb | Mar | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec |
| Research Component | Act. 1 Inter American Journal |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 2 Inventory of existing research and research institutions |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 State of the art on evaluation and assessment of programs and policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Publication on priority topic identified by Advisory Board |  |  |  |  |  |  |  |  |  |  |  |  |
| Professional Development and Educational Resources | Act 1. Regional Distance Course for Teachers: (Peru) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 2. Education for Democratic Citizenship in the Caribbean: A distance course for educators |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 Publication on teaching democratic values and practices |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Video and media series on democratic pedagogy (developing proposal) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 5. Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal) |  |  |  |  |  |  |  |  |  |  |  |  |
| Information Exchange | Act. 1 web portal, on-line bulletin, and brochure |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 2. Portfolio of Promising Initiatives |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 4. Advisory Board meetings |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 5 Two Information exchange workshops on policies and practices |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Months | 2009 |
| --- | --- | --- |
| Component | Weeks |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Jan | Feb | Mar | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec |
| Research Component | Act. 1 Inter American Journal |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 2 Inventory of existing research and research institutions |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 State of the art on evaluation and assessment of programs and policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Publication on priority topic identified by Advisory Board |  |  |  |  |  |  |  |  |  |  |  |  |
| Professional Development and Educational Resources | Act 1. Regional Distance Course for Teachers: (Peru) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 2. Education for Democratic Citizenship in the Caribbean: A distance course for educators |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 Publication on teaching democratic values and practices |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Video and media series on democratic pedagogy (developing proposal) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 5. Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal) |  |  |  |  |  |  |  |  |  |  |  |  |
| Information Exchange | Act. 1 web portal, on-line bulletin, and brochure |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 2. Portfolio of Promising Initiatives |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 3. Advisory Board meetings |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Two Information exchange workshops on policies and practices |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Months | 2010 |
| --- | --- | --- |
| Component | Weeks |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Jan | Feb | Mar | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec |
| Research Component | Act. 1 Inter American Journal |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 2 Inventory of existing research and research institutions |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 State of the art on evaluation and assessment of programs and policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Publication on priority topic identified by Advisory Board |  |  |  |  |  |  |  |  |  |  |  |  |
| Professional Development and Educational Resources | Act 1. Regional Distance Course for Teachers: (Peru) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 2. Education for Democratic Citizenship in the Caribbean: A distance course for educators |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 3 Publication on teaching democratic values and practices |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Video and media series on democratic pedagogy (developing proposal) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 5. Promoting Tolerance and Diversity in the Americas: Radio and video series (developing proposal) |  |  |  |  |  |  |  |  |  |  |  |  |
| Information Exchange | Act. 1 web portal, on-line bulletin, and brochure |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 2. Portfolio of Promising Initiatives |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act 3. Advisory Board meetings |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Act. 4 Two Information exchange workshops on policies and practices |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  |  |  |  |  |  |  |  |  |

Background:

The Inter-American Program on Education for Democratic Values and Practices responds to mandates from the Summits and ministerial processes relating to the promotion of a democratic culture through education./  Within the education ministerial process, the idea of creating a hemispheric-wide program in education for democratic values first emerged at the II Meeting of Ministers in Uruguay in 2001. At the III Meeting of Ministers of Education held in Mexico in 2003, ministers reiterated their commitment to create a hemispheric program in this area and instructed the CIE to organize a meeting on the topic of education for democracy. In response, the OAS organized a special joint meeting of the Permanent Council (PC) and the CIE in April of 2004.  Experts in education for democracy from both the formal and non formal education sectors were invited to the PC/CIE meeting to share and analyze current initiatives in education for democracy throughout the hemisphere and to develop specific guidelines to develop a hemispheric program. In follow-up, working groups within the CIE and the Permanent Council were formed in order to develop a program around the guidelines established in the April 2004 session. The final proposal for the Inter American Program was adopted at the IV Meeting of the Ministers of Education through Resolution 12 (CIDI/RME/RES. 12 (IV-O/05).

Annex II:  Recommendations Advisory Board for Inter American program on Democratic Values and Practices by component

RESEARCH COMPONENT

SUMMARY OF RECOMMENDATIONS

- Compile a list of all available research publications and unpublished research reports on the topic in at least the last five years.

- Commission or seek to develop an annotated bibliography on research findings regarding citizenship education and make this information public in an effective way.

- Commission a state of the art document on research in citizenship education during at least the last five years and widely disseminate the document

- Create monitoring mechanisms, including cross-cultural indicators or parameters of citizenship health, to show the way countries are meeting the benchmarks set for citizenship education in their policy mandates

- Support new research, including cross-sectional and longitudinal studies. Should consider addressing different levels of analysis (societal, institutional and individual levels) in order to provide relevant information for different users (teachers, policy makers, etc.)

- Identify and select existing relevant citizenship education projects, assess their strengths and weaknesses and their potential for replication.

- Facilitate and encourage the use of a variety of research approaches and methodologies.

- Monitor and provide periodic incentives or recognition to research experiences developed within educational centers (schools, universities, etc.) or by members of the educative community (teachers, students, parents, etc).

- Promote the creation of a citizenship education research network (including universities, research centers and individual researchers).

PROFESSIONAL DEVELOPMENT AND EDUCATIONAL RESOURCES COMPONENT

SUMMARY OF RECOMMENDATIONS

- Compile information on the supply of training in democratic values and development of citizenship (for teachers, local leaders, students, etc.)   that exists in countries in the region (state of the art)

- Identify practices that transform educational actors into subjects of their own formation.

- Favor the incorporation of formation in democratic values in the national plans of pre and in-service teacher training.

- Emphasize the following key areas: a) reflection of professional practice (self observation, team or expert observation); b) construction of a cooperative paradigm of professional learning that goes beyond the traditional model of isolated networks; c) transformation of professional practice through an analysis of documented experiences.

- Promote the articulation and complementarities of initiatives of  international organizations, governments and civil society around the preparation and practice of teachers (i.e. Observatory IDB)

- Facilitate meetings among teachers for the exchange of practices in courses that favor democratic values in living together in the school

- Offer countries of the region a resource bank in order to facilitate professional development.

- Offer countries of the regions contents, methodologies, and resources (videos, publications, CDs, etc.) for the training of student leaders who can appropriate and disseminate democratic values.

- Favor opportunities for meeting and exchange among program protagonists.

INFORMATION EXCHANGE COMPONENT

SUMMARY OF RECOMMENDATIONS

The group developed a framework that captures both the spirit and concepts expressed by the four groups. The framework consists of three connected process that we recommend be developed in order to achieve our vision and mission.

1.	Networking

By organizing and taking advantage of activities, opportunities and forums.

- Within Inter-American program

- Within sub-regions

- External to the program

With various entry points for individuals, groups and networks

- Create and share products, resources, research summaries, information on policies, professional development and emerging issues.

To :  	Increase policies

Increase quality practice                    	for positive impacts on student citizenship,

Increase infrastructure 			knowledge, skills and dispositions

Increase capacity

- Disseminate information to policy makers, education leaders and other stakeholders.

- How they want it

- When they want it

- In the language they want it

# Footnotes

.	Details on the Program’s objectives and components in CIDI/RME/RES.12 (IV-O/05)

.	This report will seek to complement and not duplicate the efforts of the Inter American Development Bank’s regional Observatory on Citizenship Education coordinated by National Ministry of Education of Colombia and with participation of 7 OAS member states.

.	The scope of this external evaluation is contingent upon the amount and source of funds executed by the Program.

.	The Declaration of Quebec City, adopted at the Third Summit of the Americas (2001), and the Declaration of Nuevo León of the Special Summit of the Americas (2004) recognize the fundamental importance of the values and practices of democracy; and the Declarations of these Summits recognize that education is key to strengthening democratic institutions.  Most recently, the Declaration of Nuevo León states the importance of promoting a culture and education for democracy. In addition there are several mandates that make specific reference to promoting a democratic culture through education and these include, AG/RES. 2119 (XXXV-O/05), AG/RES. 2045 (XXXIV-O/04), AG/RES. 2044 (XXXIV-O/04), AG/RES. 1960 (XXXIII-O/03), AG/RES. 1907 (XXXII-O/02), and AG/RES. 1869 (XXXII-O/02).

# Text boxes

ORGANIZATION OF AMERICAN STATES

Inter-American Council for Integral Development

(CIDI)

cidi01673e01