## INGLES
Annex 1
UPDATE PRESENTED BY THE OAS DEPARTMENT OF EDUCATION AND CULTURE ON THE EXECUTION OF THE CIC WORK 2005-2007
SUMMARY CHART: MANDATES IN CULTURE, ACTIVITIES AND ALLOCATION OF RESOURCES
(Presented during the Preparatory Meeting for the Third Inter-American Meeting of Ministers of Culture and Highest Appropriate Authorities)
Washington, D.C. August 17-18, 2006
|  | Themes | Status | Activities | Description | Other sources | OAS Sub fund allocation of resources | Expenses (as of July 31, 2006) | Resources Available
Preservation and protection of cultural heritage
|  |  | Completed | Workshop Mexico | Experience sharing workshop on Integral Community Conservation and Development Projects, held September 2005. | Mexico, OAS Scholarships | 8224.18 | 8224.18 | 0
|  |  | First Quarter 2007 | Regional Workshops: Defending cultural heritage (Proposed by the US) | Sub regional Workshops to promote exchange of ideas, experiences and information on successes and opportunities in the protection against looting of cultural heritage. | To be defined - US | 32000 |  | 32000
|  |  | On hold | Sister Parks of the Americas (Proposal presented by the US) | Conference to put in place a framework of action to support partnerships among world heritage and world class cultural sites. | To be defined - US | 0 | 0 | 0
Cultural identity, diversity and dignity
|  |  | 2007 | Seminar / To be hosted by Brazil | Regional seminar on cultural diversity. Brazil will submit a proposal taking into account the interests of member States. | To be defined - Brazil | 20000 | 0 | 20000
|  |  | 2007 | Seminar / Proposed by Jamaica | Education and culture / An event that brings together education and culture authorities to consider ways to promote dignity, diversity and identity through the inclusion of cultural content in education. Jamaica will develop a proposal to be presented to CIC Authorities / Time frame 2007 | To be defined |  |  | No resources have been allocated
Culture and the creation of decent jobs and overcoming poverty
|  |  | Completed | Workshop Canada | Young Canada Works, held October 2003 | Canada | 0 |  | 0
|  |  | Last quarter 2006 | Workshop Honduras | Experience sharing workshop on Honduras's Program of Rescue and Promotion of the Artisan, Indigenous and Traditional Production of Honduras (PROPAITH). The OAS Department of Scholarships granted 10 scholarships. OAS Technical Secretariat and Honduras authorities working on program and defining agenda and dates. | Honduras, OAS Scholarships | 10000 |  | 10000
Cultural information systems
|  |  | Completed | Workshop in Central America (Mexico) | Share experiences of Mexico and Central American countries. Held: July 2006, Mexico | Mexico | 24000 | 16998.91 | 7001.09
|  |  | Completed | Workshop in the Caribbean (Canada) | Share experiences of Canada and Caribbean countries. Held: March 2006, Port of Spain, Trinidad & Tobago. | Canada | 4000 | 3822 | 178
|  |  | Sept. 14-15, 2006 | Workshop Andean Region and the southern cone (Chile-CAB) | To share experiences of South American countries. Programmed: September 13-14, 2006, Valparaiso, Chile. CAB approved $10,000 to support this activity. | Chile, Convenio Andres Bello | 4000 |  | 4000
|  |  | On going | Network of Observatories | Some members of the Network of Observatories participated in the CIS Workshop for the Caribbean and took the opportunity to meet informally to discuss next steps for the Network's virtual forum. Virtual forum to discuss Survey and future work to be defined. |  | 10000 | 0 | 10000
[5 empty] | TOTAL |  | 112224.18 | 29045.09 | 83179.09