DRAFT CONTRACT

Between

THE OWNER AND THE BUILDER

FOR

THE CONSTRUCTION OF A HOUSE

(For discussion only)

Draft contract between the Owner and the builder

for

THE CONSTRUCTION OF A HOUSE

Prepared by

Alwyn T. Wason P.Eng

for the

Meetings with builders and home owners

held in Antigua, Barbuda, St. Kitts and Nevis in March 2001

sponsored by

the Post Georges Disaster Mitigation Project

funded by

the United States Agency for International Development and

executed by

the Organization of American States

DRAFT CONTRACT BETWEEN THE OWNER AND THE BUILDER

Contents

Section 1 		 Articles of Agreement

Section 2		General Information

Section 3		Standard Conditions of Contract

SECTION 1

DRAFT ARTICLES OF AGREEMENT (For Discussion only)

ARTICLES OF AGREEMENT MADE THE 		day of 				20  .

BETWEEN

(hereinafter called “The Owner”) of the one part and

of (or whose office is situated at) 					(hereinafter called “The Builder”) of the other part.

WHEREAS the Owner is desirous of having a house and its supporting infrastructure (hereinafter called the Works) constructed in accordance with the drawings and specifications approved by the Board and in accordance with the General Information at Section 2 and the General Conditions of Contract at Section 3.

AND WHEREAS the Builder has submitted his offer dated 	day of 			20  ,

offering to complete and maintain the Works upon the said conditions and in accordance with the Drawings and Specifications.

AND WHEREAS the Owner has accepted the Builder’s offer conveyed in the said tender.

NOW IT IS HEREBY AGREED AS FOLLOWS:

(1)	For the consideration hereinafter mentioned, the Builder shall complete and maintain the Works subjected to the said Conditions of Contract and in accordance with the Drawings and Specifications.

(2) 	The Owner will pay the Builder the sum of ($ EC) __________________________

or such other sum as shall become payable in accordance with the said Conditions of Contract for the construction, completion, and maintenance of the Works.

IN WITNESS hereof the parties have signed in the presence of the subscribing witness,

Signed for and on behalf of the Owner by:

___________________________________________________________

SIGNATURE OF OWNER OR AGENT

In the presence of:

_____________________________________________________________

Witness

_____________________________________________________________

SIGNATURE OF BUILDER

In the presence of:

_____________________________________________________________

Witness

Date:_________________________________________________________

SECTION 2

GENERAL INFORMATION

2.1	This draft of a contract between the Owner and the Builder is intended to be used for the construction of small houses which are within the scope of the Building Guidelines. Buildings outside the scope of the Building Guidelines are more complicated and any agreement between the Owner and the Builder should be made using the standard agreements drafted by the major architectural and engineering institutions of the UK. USA, Canada, or Europe.

2.2	A standard contract for the construction of a house will contain drawings and specifications as approved by the Board, General Conditions for the execution of the Works which include the house itself and the exterior works such as the septic tank, drainage, water cistern, access roads and landscaping where required.

2.3	This draft assumes that:

2.3.1	A person (the Owner) wishes to construct a house and has purchased or owns land suitable for the construction of a house.

2.3.2	A designer has been engaged by the Owner to draw up plans for the house.

2.3.3	The plans drawn are in accordance with the requirements of the Board and the relevant Regulations in all respects, and include adequate information on items such as the structure of the building, electricity, plumbing, septic tank, drainage, water cistern and guttering, access roadways, landscaping and descriptions of the materials to be used.

2.3.4	The plans include adequate information (specifications) on the materials to be used so that the Owner or the Builder can purchase the materials for the house. Such descriptions or specifications, can be noted on the plans or in a separate document.

2.3.5	The plans have been approved by the Owner.

2.3.6	The plans have been approved by the Board.

2.3.7	The designer, the Owner or the Owner’s representative will be required to inspect the construction to ensure that the Builder carries out the work in accordance with the plans approved by the Board

2.3.8	The Builder will be asked by the Owner to provide a price for constructing the house in accordance with the approved plans and the price will include all material tools and equipment and labour needed to construct the house including all interior and exterior Works, unless the Owner decides in writing that certain parts of the Works will not be carried out by the Builder.

2.4	The agreement between the Owner and the Builder will not be in force until the Board has approved the plans for the construction of the house.

SECTION 3

STANDARD CONDITIONS OF CONTRACT

3.1	Commencement of the works

3.1.1	Date of signing of the contract: __________________________________

3.1.2	Date of occupying the site by the Builder: ___________________________

3.2	Date of completion of the Works: ______________________________________

3.3	Minimum number of workmen on the site: _______________________________

3.4	Variations and alterations

3.4.1	The Owner has the right to request the Builder to carry out all variations and alterations from the plans and specifications provided that such alterations and variations have been approved by the Board in accordance with the controlling legislation.

3.4.2	The Builder shall price such variations and alterations within a reasonable amount of time of the receipt of the requests by the Owner to do so. Work shall not be carried out on the alterations and variations until the Owner and the Builder have agreed to the prices charged by the Builder for such work.

3.4.3	The Builder shall state whether the alterations or variations requested will lead to an extension of time for the completion of the Works and he/she shall give the Owner his/her best estimate of the extra time required.

3.5.	Extension of time

3.5.1	As soon as the Builder recognises that the work will not be finished in the time agreed upon, he/she shall inform the Owner of the need for more time to complete the Works and the reason for the request for the increased time.

3.5.2	It is the duty of the Owner to consider the request for an extension of the contract time taking into account the reasons given by the Builder for such extension, and to grant the request if considered reasonable in the circumstances of the construction of the Works.

3.6.	Maintenance period

The Builder is expected to make right any defects found in the Works for a period of up to six months after the completion of the Works and the granting of a Certificate of Occupancy by the Board.

3.7.	Relations between the Builder and the Owner

3.7.1	The Builder shall carry out the Works in accordance with the drawings and specifications and in accordance with any reasonable instructions by the Owner or his/her representative.

3.7.2	As soon as possible after the signing of the contract between the Owner and the Builder, the Owner shall inform the Builder the name of his/her authorised representative who will represent the Owner for the construction of the Works.

3.7.3	As soon as possible after the signing of the contract the Builder shall inform the Owner in writing the name of the person who shall be authorised by the Builder to represent the Builder for the construction of the Works.

3.7.4	The Owner and the Builder shall inform each other in writing when there is a change of the persons authorised to represent them for the construction of the Works.

3.7.5	All instructions from the Owner or his/her representative shall be given to the Builder or his/her representative in writing.

3.8.	Payment schedule.

The Owner shall pay to the Builder the following percentages of the total cost of the contract for the Works as agreed upon between the Builder and the Owner.:

3.8.1	On the signing of the contract a sum sufficient to bring the payments up to not more than 5  percent depending on the agreed arrangements between the Owner and the Builder

3.8.2	On the completion of the foundations a sum sufficient to bring the payments up to  not more than a total of 10 percent

3.8.3	On completion of the walls up to and including the ring beams a sum sufficient to bring the payments up to not more than 20 percent

    - On completion of the roofs including the roof sheeting and guttering and the installation of hurricane clips a sum sufficient to bring the payments up to not more than 30 percent

3.8.5	Upon completion of the interior and exterior plastering and installation of doors and window frames not including painting a sum sufficient to bring the payments up to not more than 40 percent

3.8.6	Upon completion of the interior works such as:

-	the ceiling,

-	plumbing and plumbing fixtures,

-	electrical wiring,

-	all carpentry counter tops and cupboards, and

-	tiling

a sum sufficient to bring the payments up to not more than 60 percent

3.8.7	Upon completion of construction of water cistern or tank where required, the septic tank and soakaway or tile field, permanent water supply services and all other plumbing requirements a sum sufficient to bring the payments up to not more than 70 percent.

3.8.8	Upon completion of the contract for the Works including:

-	installation of doors and windows

-	all other interior and exterior finishes including tiling

-	painting interior and exterior

-	the approval of the electrical wiring and fittings by the electricity supplier,

-	landscaping where required, and

- 	cleanup of the site,

a sum sufficient to bring the payments up to not more that 90 percent.

3.8.9	Upon the expiry of the maintenance period, the remaining sum of 10 percent.